## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-1-2b_Keyboard Warriors
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user I want to enter my username and login so that I can view the information I have access to based on my access level. | **Given** a user is on the log in page, **when** enter an existing username **then** I expect to be logged into that user account and be able to view the shopping cart that is assigned to that user. . |  | AB, 3/23/2023, passed
| **Given** a user in on the log in page, **when** admin is entered as a username, **then** I expect to be logged in as the admin who can adjust inventory and view total order history for whole e-store. |  | AB, 3/23/2023, passed
| **Given** a user is on the log in page, **when** a username that does not exist already is entered, **then** i expect to be prompted to create a user with that username. |  | AB, 3/23/2023, passed
As an Admin I want to add to the inventory so that new products can be available to customers. | **Given** that I am an Admin, **when** I create a keyboard object with various attributes, **then** that Keyboard object will be added to the inventory. |  | AP, 3/23/2023, passed
As an Admin, I want to be able to remove Keyboards from inventory so that I can let customers know which items are no longer being sold. | **Given** the Keyboard object already exists in the inventory **when** I specify that Keyboard **then** it will be deleted from the inventory . |  | KB, 3/22/23, passed
As an Admin I want to edit existing Keyboard objects in the inventory so that customers can view an updated list of products. | **Given** some Keyboard object **when** I change one or more of its attributes, **then** the inventory will be updated with those changes. |  | KB, 3/22/23, passed
As a Customer I want to create a user account so that purchase items from the website. | **Given** that an account with the entered username doesnt exist **when** create a user account with that username **then** a User object created with that username |  | JR, 3/22/23, passed
As a Customer I want a shopping cart object created so that purchase items from the website. | **Given** that an account with the entered username doesnt exist **when** create a user account with that username **then** an empty shopping cart will be created and stored in that User object |  | AY, 3/23/23, passed
As a Customer I want to view my order history so that i can see what I've purchased from the store before. | **Given** that an account with the entered username doesnt exist **when** create a user account with that username **then** an empty order history list will be created and stored in that User object |  | AY, 3/23/23, passed
As a Customer I want to be able to browse the inventory of keyboards so that I can place ones I would like to purchase into my shopping cart. | **Given** I am logged in as a user **when** navigate to the inventory page **then** I expect to view the inventory of keyboards |  | AP, 3/23/2023, passed
As a customer I want to be able to search through the inventory for specific keyboards so that I can purchase specific keyboards Search by keyboard name. | **Given** I am logged in as a customer user **when** I enter in some criteria for keyboards**then** I expect a list of keyboards that match those criteria. |  | AP, 3/23/2023, passed
As a CUSTOMER I want to be able to VIEW MY SHOPPING CART so I can SEE WHAT KEYBOARDS IM LOOKING TO PURCHASE. | **Given** that I'm logged in as a customer user **when** I click the shopping cart view **then** I expect a shopping cart view page where I can see a list of keyboards that are in my shopping cart. |  | AY, 3/23/23, passed
As a customer I want to be able to add keyboards to my shopping cart so that I can purchase them. | Given that I am logged into a customer account, when I add an item to my shopping cart, the item is added to my user shopping cart list. |  | JR, 3/23/23, passed
| Given that I am logged into a customer account, when I add an item to my shopping cart, that item appears on my shopping cart page. |  | JR, 3/23/23, passed
As a customer, I want to be able to remove items from my shopping cart so that I can choose not to purchase them anymore. | Given that I am logged into a customer account and my shopping cart as an item in it, when I click on the remove item button in the shopping cart page, that item should be removed from my shopping cart list |  | AY, 3/23/23, passed
| Given that I am logged into a customer account and my shopping cart as an item in it, when I click on the remove item button in the shopping cart page, that item should be removed from my shopping cart page on the website. |  | AY, 3/23/23, passed
SPRINT 3
As a admin, I want to view a central page where I can add keyboards, remove keyboards, or edit keyboard listings so that the admin can adjust what is available for purchase. | Given an admin is logged in, then a button on the navbar will appear that allows the admin to view a condensed inventory.
Given an admin is logged in and the edit inventory page is pulled up, when I create a new keyboard then I expect a keyboard with such information to be added to the inventory and displayed on the website.
Given a customer is logged in, when I am on the browse inventory page then I should not be able to see the edit inventory button
As a customer, I want to be able to remove items from my shopping cart so that I can choose not to purchase them anymore. | Given that I am logged into a customer account and my shopping cart as an item in it, when I click on the remove item button in the shopping cart page, that item should be removed from my shopping cart list
Given that I am logged into a customer account and my shopping cart as an item in it, when I click on the remove item button in the shopping cart page, that item should be removed from my shopping cart page on the website.
As a user, I want to filter through the inventory by size, keycap color, switch type, and price so that I can purchase a keyboard that best fits my needs. | **Given** a user is viewing the inventory **when** enter in some search criteria **then** to see a list of keyboards that match that criteria.
As a user, I want to filter through the inventory by size, keycap color, switch type, and price so that I can purchase a keyboard that best fits my needs. | **Given** a user is viewing the inventory **when** enter in some search criteria **then** to see a list of keyboards that match that criteria.
As a user, I want the keyboards that I have purchased in the past to be saved to my username so that I can see what I have previously purchased. | Given a user is logged in, when I purchase a keyboard then that keyboard object should be stored in my order history.
As a customer, I want to view what keyboards I have purchased in the past so that I can avoid repurchasing the same keyboard. | Given that a user is logged in and has purchased a keyboard previously, when I click the order history button, I expect to be taken to a page where I can view what keyboards I have purchased in the past.
As a user, I want to check out the items that are in my shopping cart so that they are added to my history. | Given a shopping cart full of items when I hit the check out button then I expect the keyboards be added to my order history.
Given a shopping cart full of items, when I hit the check out button then I expect the keyboard inventory to update.
As a user, I want to filter through the inventory by size, keycap color, switch type, and price so that I can purchase a keyboard that best fits my needs. | **Given** a user is viewing the inventory **when** enter in some search criteria **then** to see a list of keyboards that match that criteria.
As an admin, I want to add keyboard objects with size, color, and switch type so that I can be more specific with what keyboards I'm selling | Given I am logged into the system, when I add a keyboard to the inventory then i expect the system to ask for size, switch, color, price, quantity, and name.
As a user I want to customize the keyboard size, switch type, and color so that I can select a keyboard that better fits my needs. | Given a user is logged in, when I select a keyboard and change its size, a new keyboard object should be created with that size and be added to my shopping cart.
Given a user is logged in, when I select a keyboard and change its switch type, a new keyboard object should be created with that switch and be added to my shopping cart.
Given a user is logged in, when I select a keyboard and change its keycap color, a new keyboard object should be created with that cap color and be added to my shopping cart.